## Gantt Chart
Annex 9 - Government Registration and RSD system
This Gantt chart is a "living document" and will be updated frequently as the project progresses.
No | TASK TITLE | TASK OWNER | FECHA DE INICIO | FECHA DE VENCIMIENTO | DURACION | PERCENTAGE OF COMPLETE TASK | PHASE ZERO COMPLETION | [23 empty] | PHASE ONE COMPLETION | [7 empty] | PHASE TWO COMPLETION | [15 empty] | PHASE THREE COMPLETION | [7 empty] | PHASE FOUR COMPLETION
[11 empty] | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
1 | REG (3-4 Months) | [5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.1 | Mapping Current Process Flow |  |  |  |  | 100% | bar: W1 to W2
1.2 | Mapping Current Data Flow |  |  |  |  | 100% | bar: W1 to W2
1.3 | Mapping the different Databases |  |  |  |  | 100% | bar: W1 to W2
1.4 | Analyze the different Databases |  |  |  |  | 50% | bar: W1 to July W1
1.5 | Analyze system X and database |  |  |  |  | 100% | bar: W1 to W4
1.6 | Decide tool modality |  |  |  |  | 100% | bar: W1 to W2
1.8 | Analyze Delays |  |  |  |  | 100% | bar: W1 to W3
1.9 | Review the backlog of physical files pending scanning |  |  |  |  | 100% | bar: W1 to W4
1.10 | Define the datasets and tool for the digitization process |  |  |  |  | 100% | bar: W1 to W4
1.11 | Develop a quick log data entry tool |  |  |  |  | 100% | bar: W4
1.12 | Implementation of data entry for digitization of the physical file |  |  |  |  | 50% | bar: W4 to February W4
1.13 | Develop a simple staging system of appointments |  |  |  |  | 0% | bar: July W1 to July W2
1.14 | Review shared requirements |  |  |  |  | 50% | bar: W1 to May W3
1.15 | Design business requirements |  |  |  |  | 90% | bar: W4 to May W4
1.16 | Design the technical requirements |  |  |  |  | 80% | bar: W4 to May W4
1.17 | Define new process in new system |  |  |  |  | 50% | bar: W4 to July W4
1.18 | Recruitment of a development company |  |  |  |  | 0% | bar: May W4 to July W3
1.19 | Recruitment business requirements |  |  |  |  | 0% | bar: May W4 to July W3
1.20 | Define server needs |  |  |  |  | 50% | bar: July W3 to August W1
1.21 | Develop tool (online self-registration that includes programming and interoperability with system X and card issuance) |  |  |  |  | 0% | bar: July W4 to November W3
1.22 | Map Reports |  |  |  |  | 0% | bar: August W2 to September W1
1.23 | Design card issuance and online renewal |  |  |  |  | 0% | bar: August W1 to August W4
1.24 | Define Security Model |  |  |  |  | 0% | bar: August W3 to September W2
1.25 | User Access |  |  |  |  | 0% | bar: September W3 to September W4
1.26 | Continuous Business Analysis |  |  |  |  | 0% | bar: August W1 to September W4
1.27 | Test Application |  |  |  |  | 0% | bar: November W1 to November W2
1.28 | Review the Flow of the Registration Process in the Shelter Unit |  |  |  |  | 80% | bar: W3 to July W3
1.29 | Review the Registration and Staffing Floor Plan |  |  |  |  | 80% | bar: W3 to July W3
1.30 | Define the material needs for a new process (tables, chairs, dividers, ticket system, computers, etc.) |  |  |  |  | 90% | bar: W1 to May W3
1.31 | Train staff on new tools and new processes |  |  |  |  | 0% | bar: November W3 to November W4
1.32 | Referral Training |  |  |  |  | 0% | bar: November W3 to November W4
1.33 | Specific Needs Training |  |  |  |  | 0% | bar: November W1 to November W2
1.34 | Prepare information campaign for PoCs on new process |  |  |  |  | 0% | bar: August W4 to November W2
1.35 | Define Communication/Notification System To English  Define Communication/Notification System To English  Define Communication/Notification System Define Communication/Notification System |  |  |  |  | 0% | bar: August W1 to September W4
1.36 | Develop SOPs |  |  |  |  | 0% | bar: September W3 to November W2
1.37 | Improve Reports for System X and Improve The System |  |  |  |  | 0% | bar: July W3 to July W4
2 | RSD in First Instance
2.1 | Define new process in new system |  |  |  |  | 0% | bar: August W1 to December W1
2.2 | Define dataset for RSD module |  |  |  |  | 0% | bar: September W1 to December W1
2.3 | Notifications |  |  |  |  | 0%
2.4 | Develop a new process in a new system |  |  |  |  | 0% | bar: December W2 to January W1
2.5 | Develop Templates
2.6 | Train staff on new tools and new processess | bar: January W3 to January W4
2.7 | SOPs | bar: December W3 to January W2
2.8 | Design business requirements | bar: November W1 to December W1
2.9 | Design the technical requirements | bar: November W1 to December W1
2.10 | Develop RSD Module in 1st Instance | bar: December W2 to January W2
2.11 | Define Security Model | bar: November W4 to December W2
2.12 | User Access | bar: December W4 to January W2
2.13 | Test Application | bar: January W1 to January W2
3 | RSD in Second Instance
3.1 | Define new process in new system |  |  |  |  | 0% | bar: December W2 to January W3
3.2 | Define dataset for RSD module in Second Instance |  |  |  |  | 0% | bar: December W4 to February W1
3.3 | Develop a new process in a new system
3.4 | Design business requirements | bar: February W4 to March W2
3.5 | Design the technical requirements | bar: February W4 to March W2
3.6 | Improve the current system/develop a new module (to be defined) | bar: March W3 to May W1
3.7 | Develop interoperability | bar: April W2 to April W4
3.8 | Develop Templates | bar: April W2 to April W4
3.9 | Train staff on new tools and new processes | bar: May W4
3.10 | Define Security Model | bar: April W3 to May W1
3.11 | User Access | bar: May W2 to May W3
3.12 | Develop SOPs | bar: May W1 to May W3
4 | Biometric
4.1 | Obtain the specifications of the Biometrics Project | bar: November W2 to November W4
4.2 | Analyze the current process and requirements | bar: January W3 to February W2
4.3 | Design Process | bar: March W1 to March W4
4.4 | Decide on the supplier - or develop new? | bar: January W3 to January W4
4.5 | Integration of Biometrics in the System | bar: May W1 to June W1
4.6 | Launch of Biometrics | bar: June W2 to July W2
4.7 | Training on Biometrics | bar: July W3 to July W4
5 | Staffing
5.1 | ODM/IM Staff
5.2 | Registration
5.3 | Developer
5.4 | Coordinator/Administrator
5.5 | Eligibility Officer
5.6 | Registration and Eligibility Supervisor
5.7 | QAI RSD and Data Management/REG
5.8 | Technical support staff

## Output (hidden)
Registration Output
Staff | 24 | Cases per hour |  | 3 | 4 | 5 | 6 | 7
h worked | 6 | performance |  | 432 | 576 | 720 | 864 | 1008
tot h per day | 144 | backlog reduction per day (600 New arrivals per day) |  | -168 | -24 | 120 | 264 | 408
600
Backlog reduction time (60000 pending assumption - 5 days a week)
|  | 21.75 |  | -3654 | -522 | 2610 | 5742 | 8874
per months required
|  | 140000 |  | -38.3142 | 243.0556 | 53.6398 | 24.3817 | 15.7764
|  | 130000 |  | -35.5774 | -249.0421 | 49.8084 | 22.6402 | 14.6495
|  | 120000 |  | -32.8407 | -229.8851 | 45.977 | 20.8986 | 13.5227
|  | 110000 |  | -30.104 | -210.728 | 42.1456 | 19.1571 | 12.3958
|  | 100000 |  | -27.3673 | -191.5709 | 38.3142 | 17.4155 | 11.2689
|  | 90000 |  | -24.6305 | -172.4138 | 34.4828 | 15.674 | 10.142
|  | 80000 |  | -21.8938 | -153.2567 | 30.6513 | 13.9324 | 9.0151
|  | 70000 |  | -19.1571 | -134.0996 | 26.8199 | 12.1909 | 7.8882
|  | 60000 |  | -16.4204 | -114.9425 | 22.9885 | 10.4493 | 6.7613
|  | 50000 |  | -13.6836 | -95.7854 | 19.1571 | 8.7078 | 5.6344
|  | 40000 |  | -10.9469 | -76.6284 | 15.3257 | 6.9662 | 4.5076
|  | 30000 |  | -8.2102 | -57.4713 | 11.4943 | 5.2247 | 3.3807
|  | 20000 |  | -5.4735 | -38.3142 | 7.6628 | 3.4831 | 2.2538
Biometrics and photo capturing step
|  |  | cases per hour | hours required
|  | 2min per case | 30 | 14.4 | 19.2 | 24 | 28.8 | 33.6
|  | 3min per cases | 20 | 21.6 | 28.8 | 36 | 43.2 | 50.4
|  | 4min per case | 15 | 28.8 | 38.4 | 48 | 57.6 | 67.2
Biometric points required
|  | 2min per case | 30 | 1.0286 | 1.3714 | 1.7143 | 2.0571 | 2.4
|  | 3min per cases | 20 | 1.5429 | 2.0571 | 2.5714 | 3.0857 | 3.6
|  | 4min per case | 15 | 2.0571 | 2.7429 | 3.4286 | 4.1143 | 4.8
Admission point
|  |  | cases per hour | hours required
|  | 1min per case | 60 | 7.2 | 9.6 | 12 | 14.4 | 16.8
|  | 2min per case | 30 | 14.4 | 19.2 | 24 | 28.8 | 33.6
|  | 3min per case | 20 | 21.6 | 28.8 | 36 | 43.2 | 50.4
Admission points required
|  | 1min per case | 60 | 0.51429 | 0.68571 | 0.85714 | 1.0286 | 1.2
|  | 2min per case | 30 | 1.0286 | 1.3714 | 1.7143 | 2.0571 | 2.4
|  | 3min per case | 20 | 1.5429 | 2.0571 | 2.5714 | 3.0857 | 3.6

## Sheet1 (hidden)
Registration Output
Staff | 36 | Cases per hour |  | 3 | 4 | 5 | 6 | 7
h worked | 6 | performance |  | 648 | 864 | 1080 | 1296 | 1512
tot h per day | 216 | backlog reduction per day (600 New arrivals per day) |  | 48 | 264 | 480 | 696 | 912
600
Backlog reduction time (60000 pending assumption - 5 days a week)
|  | 21.75 |  | 1044 | 5742 | 10440 | 15138 | 19836
per months required
|  | 140000 |  | 134.0996 | 162.037 | 13.41 | 9.2482 | 7.0579
|  | 130000 |  | 124.5211 | 22.6402 | 12.4521 | 8.5877 | 6.5537
|  | 120000 |  | 114.9425 | 20.8986 | 11.4943 | 7.9271 | 6.0496
|  | 110000 |  | 105.364 | 19.1571 | 10.5364 | 7.2665 | 5.5455
|  | 100000 |  | 95.7854 | 17.4155 | 9.5785 | 6.6059 | 5.0413
|  | 90000 |  | 86.2069 | 15.674 | 8.6207 | 5.9453 | 4.5372
|  | 80000 |  | 76.6284 | 13.9324 | 7.6628 | 5.2847 | 4.0331
|  | 70000 |  | 67.0498 | 12.1909 | 6.705 | 4.6241 | 3.5289
|  | 60000 |  | 57.4713 | 10.4493 | 5.7471 | 3.9635 | 3.0248
|  | 50000 |  | 47.8927 | 8.7078 | 4.7893 | 3.3029 | 2.5207
|  | 40000 |  | 38.3142 | 6.9662 | 3.8314 | 2.6424 | 2.0165
|  | 30000 |  | 28.7356 | 5.2247 | 2.8736 | 1.9818 | 1.5124
|  | 20000 |  | 19.1571 | 3.4831 | 1.9157 | 1.3212 | 1.0083
Biometrics and photo capturing step
|  |  | cases per hour | hours required
|  | 2min per case | 30 | 21.6 | 28.8 | 36 | 43.2 | 50.4
|  | 3min per cases | 20 | 32.4 | 43.2 | 54 | 64.8 | 75.6
|  | 4min per case | 15 | 43.2 | 57.6 | 72 | 86.4 | 100.8
Biometric points required
|  | 2min per case | 30 | 1.5429 | 2.0571 | 2.5714 | 3.0857 | 3.6
|  | 3min per cases | 20 | 2.3143 | 3.0857 | 3.8571 | 4.6286 | 5.4
|  | 4min per case | 15 | 3.0857 | 4.1143 | 5.1429 | 6.1714 | 7.2
Admission point
|  |  | cases per hour | hours required
|  | 1min per case | 60 | 10.8 | 14.4 | 18 | 21.6 | 25.2
|  | 2min per case | 30 | 21.6 | 28.8 | 36 | 43.2 | 50.4
|  | 3min per case | 20 | 32.4 | 43.2 | 54 | 64.8 | 75.6
Admission points required
|  | 1min per case | 60 | 0.77143 | 1.0286 | 1.2857 | 1.5429 | 1.8
|  | 2min per case | 30 | 1.5429 | 2.0571 | 2.5714 | 3.0857 | 3.6
|  | 3min per case | 20 | 2.3143 | 3.0857 | 3.8571 | 4.6286 | 5.4